## Slide 1: CS 2212
Introduction to Software Engineering
Chapter 25 Creating a Viable Software Plan

## Slide 2: Copyright Notice This Presentation and Its Associated Video Contain Copyright Material. This Presentation and Its Associated Video Are Provided for Teaching Purposes of CS2212 and Should Not Be Posted In Any External Site, Or Shared with. This Presentation and Its Associated Video Are Provided For Instructional Personal Use Only, and Only For The Purposes of the CS2212 Course.

## Slide 3: Part 49
Cost Estimation Concepts
An evolving system increases its complexity unless work is done to reduce it.
― Meir Lehman.
Notes: This lesson introduces the basic steps in a software engineering project at a high level.
In practice, steps often overlap.

## Slide 4: Learning Objectives in this Part
To understand the concept and the parameters that influence cost in software development estimation

## Slide 5: Process/Project Management
Project management involves a whole host of issues and skills
  Effort estimation
  Staffing
  Defining and managing the process
  Scheduling activities
  Monitoring quality
  …
Process management at the level of an organization
  A software development organization should define, implement and constantly improve their
    Software processes
    Organizational structure

## Slide 6: The four variables
The main four variables of a project
  Development cost
  Time
  Quality
  Scope
Development cost, time and quality are bad control variables
  The number of developers can only be incrementally increased (negative effects beyond the optimal count)
  Deadlines are often predetermined externally (e.g., market window, important presentation)
  Low quality upsets customers and developers
Scope is the only real control variable

## Slide 7: The “Vicious Square”
Productivity
+
+
-
-
-
-
+
+
Quality
Scope
Development time
Cost

## Slide 8: Accuracy of Estimation
Feasibility
Requirements
Design
Code
Delivery
x
2x
4x
0.25x
0.5x
As a project progresses, more information about
the progress becomes available and the accuracy
of estimation can be increased over time.
x – the actual cost of the system
Estimates on projects studied by Barry
Boehm occupied the area between the curves

## Slide 9: Estimation techniques
Expert judgement
Estimation by analogy
Parkinson's Law
Pricing to win
Top-down estimation
Bottom-up estimation
Function point estimation
Algorithmic cost modelling
©Ian Sommerville

## Slide 10: Part 50
The Function Point Metric
One accurate measurement is worth a thousand expert opinions.
― Grace Hopper.
Notes: This lesson introduces the basic steps in a software engineering project at a high level.
In practice, steps often overlap.

## Slide 11: Learning Objectives in this Part
To learn about the Function Point Metric

## Slide 12: Function Points
The idea of function point was first proposed by Albrecht in 1979.
The function point of a system is a measure of the “functionality” of the system.
Steps
  Counting the information domain – counting FPs
  Assessing complexity of the software – adjusting FPs
  Applying an empirical relationship to come up with LOC or P-months based on the adjusted FPs
This method cannot be performed automatically
©Ian Sommerville

## Slide 13: Counting Function Points

## Slide 14: Counting Function Points
User inputs. Each user input that provides distinct application oriented data to the software is counted.
User outputs. Each user output that provides application oriented information to the user is counted. Individual data items within a report are not counted separately.
User inquiries. This is an on-line input that results in the generation of some response.
Files. Each master file is counted.
External interfaces. Each interface that is used to transmit information to another system is counted.

## Slide 15: Adjusting Function Points
Answer the following questions using a scale of [0-5]: 0 not important; 5 absolutely essential. We call them influence factors (Fi).
1. Does the system require reliable backup and recovery?
2. Are data communications required?
3. Are there distributed processing functions?
4. Is performance critical?
5. Will the system run in an existing, heavily utilized operational env.?
6. Does the system require on-line data entry?

## Slide 16: Adjusting Function Points
7. Does the on-line data entry require the input transaction to be built over multiple screens or operations (user efficiency)?
8. Are the master files updated on-line?
9. Are the inputs, outputs, files, or inquiries complex?
10. Is the internal processing complex?
11. Is the code designed to be reusable?
12. Is installation included in the design?
13. Is the system designed for multiple installations?
14. Is the application designed to facilitate change and ease of use by the user?

## Slide 17: Map FPs to LOC
Use an empirical relationship
  Function point = count total  [0.65 + 0.01  (sum of the 14 Fi)]
  Companies may want to refine their own version
According to a 1989 study, implementing a function point in a given programming language requires the following number of lines of code
  Assembly 320
  C 128
  COBOL 106
  C++ 64
  Visual Basic 32
  SQL 12
See www.ifpug.org for more information on FP

## Slide 18: Example: Project X

## Slide 19: Example: Project X
Total of FPs = 25
F4 = 4, F10 = 4, other Fi’s are set to 0. Sum of all Fi’s = 8.
FP = 25 x (0.65 + 0.01 x 8) = 18.25
Lines of code in C = 18.25 x 128 LOC = 2336 LOC
In the past, students have implemented their projects using about 2500 LOC.

## Slide 20: Part 51
Algorithmic Cost Estimation: The COCOMO Model
Engineering is done with numbers. Analysis without numbers is only an opinion.
― 1st of Akin's Laws of Spacecraft Design.
Notes: This lesson introduces the basic steps in a software engineering project at a high level.
In practice, steps often overlap.

## Slide 21: Learning Objectives in this Part
To learn how to estimate software development effort and cost using the COCOMO model

## Slide 22: Algorithmic cost modelling
Cost is estimated as a mathematical function of product, project and process attributes whose values are estimated by project managers and metrics (e.g. KPIs) collected by DevOps tools.
The most commonly used product attribute for cost estimation is LOC (code size)
Most models are basically similar but are utilizing different attributes

## Slide 23: The COCOMO model
Developed at TRW, a US defence contractor
Based on a cost database of more than 60 different projects
COCOMO is provided in three different versions:
  Basic - computes a 'ball-park’ effort estimate based on product attributes
  Intermediate – Enhances the estimate provided by the Basic COCOMO version using also project and process attributes
  Advanced – Computes estimates for differ project phases and parts separately

## Slide 24: Project Types
Organic mode projects : Small teams, familiar environment, well-understood applications, no difficult non-functional requirements (EASY)
Semi-detached mode projects: Project team may have experience mixture, system may have more significant non-functional constraints, organization may have less familiarity with application (HARDER)
Embedded projects: Hardware/software systems, tight constraints, unusual for team to have deep application experience (HARD)

## Slide 25: Basic COCOMO Formula
Organic mode projects: PM = 2.4 (KDSI) 1.05
Semi-detached mode projects: PM = 3 (KDSI) 1.12
Embedded mode projects: PM = 3.6 (KDSI) 1.2
KDSI = Kilo Delivered Source Instructions

## Slide 26: Development Time Estimates
Organic: TDEV = 2.5 (PM) 0.38
Semi-detached: TDEV = 2.5 (PM) 0.35
Embedded mode: TDEV = 2.5 (PM) 0.32
Personnel requirement: N = PM/TDEV
  This last formula needs to be adjusted (see next slide)
Adapted from Ian Sommerville

## Slide 27: Basic COCOMO Assumptions
Implicit productivity estimate
  Organic mode = 16 LOC/day (averaged across the life cycle of similar projects)
  Embedded mode = 4 LOC/day (averaged across the life cycle of similar projects)
Time required is a function of total effort NOT team size

## Slide 28: Basic COCOMO Example
Organic mode project, 32KLOC
  PM = 2.4 (32) 1.05 = 91 person months
  TDEV = 2.5 (91) 0.38 = 14 months
  N = 91/15 = 6.5 people
Embedded mode project, 128KLOC
  PM = 3.6 (128)1.2 = 1216 person-months
  TDEV = 2.5 (1216)0.32 = 24 months
  N = 1216/24 = 51

## Slide 29: Intermediate COCOMO
The Intermediate version of COCOMO takes the estimates provided by the Basic COCOMO version as starting point for its computation
Takes into account different additional attributes which affect cost. Each attribute has a score and weight.
  Personnel related attributes
  Product related attributes
  Computer / infrastructure related attributes
  Project related attributes
Multiplies basic cost by attribute multipliers which may increase or decrease costs

## Slide 30: Personnel and Product Attributes
Personnel attributes
  Analyst capability
  Virtual machine experience
  Programmer capability
  Programming language experience
  Application experience
Product attributes
  Reliability requirement
  Database size
  Product complexity

## Slide 31: Computer and Project Attributes
Computer attributes
  Execution time constraints
  Storage constraints
  Virtual machine volatility
  Computer turnaround time
Project attributes
  Modern programming practices
  Software tools
  Required development schedule

## Slide 32: Attribute Choice
These are attributes which were found to be significant in most project studies
Other attributes may be more significant for other projects and is up to the organization which develops the system to assess the choice of attributes
In practice, each organization must identify its own attributes and associated multiplier values. This may come by examining past similar projects and calculating the associated multiplier values (e.g. through regression on data form past cases).

## Slide 33: Intermediate COCOMO Example
Embedded software system on microcomputer hardware.
Let us assume that basic COCOMO predicts a 45 person-month effort requirement.
Let us assume that we have applied the attributes = RELY (1.15), STOR (1.21), TIME (1.10), TOOL (1.10)
Then, the Intermediate COCOMO predicts:
  45*1.15*1.21.1.10*1.10 = 76 person-months.
Total cost = 76*$7000 = $532, 000
Adapted from Ian Sommerville

## Slide 34: Estimation methods - Summary
Function points
  SRS -> LOC
  SRS -> PM
COCOMO
  LOC -> PM
  May use FP as a front-end to COCOMO
COCOMO II
  Refined version with different estimation models based on
    Requirements (FP->PM),
    Early design (FP->PM), and
    Architecture (FP or LOC->PM)

## Slide 35: Estimation methods - Summary
Each method has strengths and weaknesses
Estimation should be based on several methods
If these do not return approximately the same result, there is insufficient information available
Some action should be taken to find out more in order to make more accurate estimates
Pricing to win is often used in situations bidding for a project (e.g. responding to a government Requests for Tenders)

## Slide 36: Your Turn
Discuss three limitations of the COCOMO model
Why using Function Points Analysis early in the project life cycle (e.g. during early requirements) is not as accurate an estimate as when performing it later in the life cycle (e.g. after architectural design)
Check-out the content of the following sites:
  https://en.wikipedia.org/wiki/Cost_estimation_in_software_engineering
  https://www.javatpoint.com/software-cost-estimation
  https://www.tutorialspoint.com/estimation_techniques/estimation_techniques_function_points.htm
  https://www.javatpoint.com/software-engineering-functional-point-fp-analysis
  https://www.geeksforgeeks.org/software-engineering-functional-point-fp-analysis/
  https://en.wikipedia.org/wiki/Function_point
  https://www.geeksforgeeks.org/software-engineering-cocomo-model/
  https://en.wikipedia.org/wiki/COCOMO